## Slide 1
Outstation Redundancy Program
Execution & Legal Alignment Overview
May 2026
CONFIDENTIAL

## Slide 2
Slide 2 — Objective
Outstation Redundancy Program | Confidential | May 2026
Objective
Execute the outstation redundancy program across multiple jurisdictions
Ensure:
  Full legal compliance by country
  Controlled and confidential execution
  Minimal operational disruption
Scope
50 Employees
across multiple regions
Multi-jurisdiction program requiring coordinated legal and HR execution across all affected countries.

## Slide 3
Slide 3 — Project Timeline (Corrected Reality View)
Outstation Redundancy Program | Confidential | May 2026
1
Phase 1
Legal Engagement
Oct 2025
Dentons formally engaged. Employee data, contracts & cases shared.
True project initiation (legal start).
2
Phase 2
Legal Structuring & Review
Oct 2025 → Apr 2026
Multi-country legal assessment.
Separation structuring & risk evaluation.
3
Phase 3
Formal Project Plan
1 Apr → 20 Apr 2026
Internal "Legal Review" phase.
4
Phase 4
Governance / Approval
21 Apr → 6 May 2026
EXCOM approval window.
5
Phase 5
Execution (Planned)
Starting 7 May 2026 onward
Full execution begins upon legal clearance + EXCOM approval.

## Slide 4
Slide 4 — Key Milestone Gap (Critical)
Outstation Redundancy Program | Confidential | May 2026
Key Observation
Legal engagement started: Oct 2025 Legal review planned completion: 20 Apr 2026
⚠ Gap Identified
No formal documented communication confirming:
Legal review completion
"Clearance to proceed"
📌 Implication
Execution depends on:
Final legal confirmation
Alignment on compliance readiness
⚠ Formal "Clearance to Proceed" confirmation is REQUIRED before execution commences

## Slide 5
Slide 5 — What "Proceed" Means
Outstation Redundancy Program | Confidential | May 2026
Executive approval is required to:
✦ Proceed with termination of identified employees
✦ Approve separation approach
✦ Approve compensation schemes (legal-backed)
"Proceed" means:
✅ Legal Clearance
+
✅ EXCOM Approval
→ Full Execution Begins

## Slide 6
Slide 6 — Execution Plan (Next Phases)
Outstation Redundancy Program | Confidential | May 2026
1
Phase 1
Legal Formalities
(Country Level)
7 May → 30 May 2026
• Local legal coordination
• Regulatory notifications
• Draft termination letters
2
Phase 2
Employee
Notification
1 Jun → 14 Jun 2026
• Issue formal notifications
• Conduct 1:1 meetings
• Provide support resources
3
Phase 3
Offboarding
15 Jun → 28 Jun 2026
• Knowledge transfer
• Equipment return
• Access revocation preparation
4
Phase 4
Final Settlement
1 Jul → 14 Jul 2026
• Process final payments
• Issue settlement agreements
• Legal sign-off
5
Phase 5
System Closure
1 Jul → 14 Jul 2026
• Revoke system access
• Archive employee data
• Close HR records

## Slide 7
Slide 7 — Roles & Ownership
Outstation Redundancy Program | Confidential | May 2026
Area
Owner
⚖
Legal Review & Compliance
Ahsan
✔
EXCOM Approval
Kumail
👥
Employee Notification & Offboarding
Hiba
💼
Final Settlements
Saif
🔒
System & Access Removal
Ridha

## Slide 8
Slide 8 — Financial Impact
Outstation Redundancy Program | Confidential | May 2026
Monthly Savings
OMR
33,281
per month
Starting from execution completion
Aug–Dec 2026 Impact
Total Projected Savings
OMR
166,405
(5 months)
Strong contribution to 2026 cost optimization targets
×5

## Slide 9
Slide 9 — Risks & Dependencies
Outstation Redundancy Program | Confidential | May 2026
🔴 Key Risks
HIGH
Lack of formal legal sign-off record
MEDIUM
Country-specific compliance delays
MEDIUM
Regulatory approval timeline overruns
🟡 Dependencies
1
Legal final confirmation
2
EXCOM decision
3
Local legal execution readiness

## Slide 10
Slide 10 — Immediate Next Steps
Outstation Redundancy Program | Confidential | May 2026
1
Legal Alignment
✅ Obtain written confirmation: "Legal review complete"
✅ Confirm "Cleared to proceed" from Dentons
2
Governance Closure
✅ Confirm EXCOM approval status
✅ Document formal sign-off
3
Execution Readiness
✅ Prepare legal documentation by country
✅ Prepare notification materials
✅ Prepare HR case handling procedures

## Slide 11
Key Message to Leadership
📅
Project initiated Oct 2025 with Dentons
📋
Structured into formal execution plan Apr–Jul 2026
🔄
Currently at transition point into execution
⚖
Final legal clearance confirmation is being aligned
Once confirmed → Immediate execution can proceed
Outstation Redundancy Program | Confidential | May 2026